## Gantt Chart w % Complete
(I got the template for this from teamgantt.com) |  | Chart looks better in Google Sheets: https://docs.google.com/spreadsheets/d/1tKdrD-FlgixCQgAnUaI6bJCn1dcwOi6Fa_AQjPTQKIA/edit?usp=sharing | [5 empty] | Note: the "days complete" and "days remaining" columns are only for the Gantt chart's functionality, don't touch them
* = an automatically calculated cell
| TASK NAME | START DATE | DAYS AFTER 3/14* | END DATE | DURATION* (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | DAYS COMPLETE* | DAYS REMAINING* | WEEK 1: 3/14-3/16 |  |  | WEEK 2: 3/17-3/23 | [6 empty] | WEEK 3: 3/24-3/30 | [6 empty] | WEEK 4: 3/31-4/6 | [6 empty] | WEEK 5: 4/7-4/13 | [6 empty] | WEEK 6: 4/414-4/20 | [6 empty] | WEEK 7: 4/21-4/22
[10 empty] | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M
First Sample Project
| Think of a better slogan | 2024-03-24 | 10 | 2024-04-15 | 23 | All of us | 100% | 23 | 0
| Update logo | 2024-03-24 | 10 | 2024-04-15 | 22 | Joe | 100% | 23 | 0
| Add finishing touches to Balsamiq | 2024-03-24 | 10 | 2024-03-24 | 0 | Alex | 100% | 1 | 0
| Remove “Questions/discussion” button | 2024-03-24 | 10 | 2024-03-24 | 0 | Alex | 100% | 1 | 0
| Add report button | 2024-03-24 | 10 | 2024-03-24 | 0 | Alex | 100% | 1 | 0
| Add a slide in the wireframe showing what the comments section looks like | 2024-03-24 | 10 | 2024-03-24 | 0 | Alex | 100% | 1 | 0
| Have anonymous option when making comments | 2024-03-24 | 10 | 2024-03-24 | 0 | Alex | 100% | 1 | 0
| Make web pages (HTML) | 2024-03-25 | 11 | 2024-04-05 | 11 | All of us | 0% | 0 | 12
| Make homepage | 2024-03-25 | 11 | 2024-04-05 | 11 | Joe | 0% | 0 | 12
| Make course page | 2024-03-25 | 11 | 2024-04-05 | 11 | Alex | 0% | 0 | 12
| Make find exam page | 2024-03-25 | 11 | 2024-04-05 | 11 | Felipe | 0% | 0 | 12
| Format web pages (CSS) | 2024-03-25 | 11 | 2024-04-05 | 11 | All of us | 0% | 0 | 12
| Make header and footer css file, homepage css file | 2024-03-25 | 11 | 2024-04-05 | 11 | Joe | 0% | 0 | 12
| Format course page | 2024-03-25 | 11 | 2024-04-05 | 11 | Alex | 0% | 0 | 12
| Format find exam page | 2024-03-25 | 11 | 2024-04-05 | 11 | Felipe | 0% | 0 | 12
| Add functionality to web pages (Javascript, jQuery(?)) | 2024-03-25 | 11 | 2024-04-05 | 11 | All of us | 0% | 0 | 12
| Make 30 second elevator pitch | 2024-04-06 | 23 | 2024-04-15 | 9 | All of us | 0% | 0 | 10
| Make report - 3-5 page writeup | 2024-04-06 | 23 | 2024-04-15 | 9 | All of us | 0% | 0 | 10
| Peer reviews and rankings(?) | 2024-04-06 | 23 | 2024-04-15 | 9 | All of us | 0% | 0 | 10
| Finalize repo | 2024-04-06 | 23 | 2024-04-15 | 9 | All of us | 0% | 0 | 10
| Make README with instructions on how to use app, put on GitHub | 2024-04-06 | 23 | 2024-04-15 | 9 | All of us | 0% | 0 | 10
| Make project recap | 2024-04-06 | 23 | 2024-04-15 | 9 | All of us | 0% | 0 | 10
| Make 10 minute presentation | 2024-04-03 | 20 | 2024-04-10 | 7 | All of us | 0% | 0 | 8
| Practice presenting presentation | 2024-04-10 | 27 | 2024-04-15 | 5 | All of us | 0% | 0 | 6